## Sheet1
Story ID | Story Title | User Story | Story Points | Priority | Sprint Assignment | Status | Conversation (Notes) | Confirmation (Acceptance Criteria)
UI-1 | Search Cars | As a customer, I want to search for available cars by type and date so that I can find the best rental option. | 5 | High | Sprint 1 | Not Started | Needs filter by car type and availability dates. | Customer can search and see accurate results matching filters.
UI-2 | Reserve Car | As a customer, I want to reserve a car online so that I can secure a booking without calling the office. | 8 | High | Sprint 1 | Not Started | Reservation form must capture dates and payment info. | Reservation details save to database and confirmation is shown.
SEC-1 | Secure Login | As a user, I want to log in securely so that my personal data is protected. | 8 | High | Sprint 1 | Not Started | Use hashed passwords and authentication checks. | Login succeeds only with valid credentials.
UI-3 | Modify Reservation | As a customer, I want to update my existing booking so that I can extend or shorten my rental period. | 5 | Medium | Sprint 2 | Not Started | Add 'Modify' button on dashboard. | Booking updates reflect instantly in records.
UI-4 | Cancel Reservation | As a customer, I want to cancel my reservation so that I can change plans if needed. | 3 | Medium | Sprint 2 | Not Started | Add confirmation prompt before canceling. | Booking removed and availability restored.
UI-6 | Account/Profile | As a customer, I want to manage my profile so that my bookings use up-to-date information. | 3 | Low | Sprint 2 | Not Started | Allow editing of contact details. | Profile updates save successfully.
REP-1 | Car Usage Report | As a manager, I want to see which cars are most rented so that I can manage fleet inventory. | 8 | High | Sprint 3 | Not Started | Include charts for car popularity. | Report shows accurate usage data.
REP-2 | Daily Rentals Report | As a manager, I want to view daily rental activity so that I can track business performance. | 5 | Medium | Sprint 3 | Not Started | Summarize bookings per day. | Daily totals display correctly.
UI-5 | View Rental History | As a customer, I want to see my rental history so that I can track past bookings. | 2 | Low | Sprint 3 | Not Started | Display previous rentals list. | History loads with accurate dates and cars.