## Cover Page
CP317A – Milestone 02
Prepared By:
GROUP 25:
Arjun Singh
Connor Davison
Hayden Gdanski
Khush Patel
Sam Oreskovic

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Priority | Sprint | Status | Conversation | Confirmation
UI-1 | Search Cars | As a customer, I want to search for available cars by type and date so that I can find the best rental option. | 5 | High | Sprint 1 | Not Started | Needs filters for car type/date availability. | Customers can search and view matching results.
UI-2 | Reserve Car | As a customer, I want to reserve a car online so that I can secure a booking without calling the office. | 8 | High | Sprint 1 | Not Started | Reservation form needs date and payment input. | Booking saved successfully and confirmation shown.
UI-3 | Cancel Reservation | As a customer, I want to cancel my reservation so that I can change my plans if needed. | 3 | Medium | Sprint 2 | Not Started | Add confirmation before cancel. | Reservation removed and car availability restored.
UI-4 | View Rental History | As a customer, I want to see my rental history so that I can track my past bookings. | 2 | Low | Sprint 3 | Not Started | Pull booking data from user profile. | Past rentals displayed correctly.
UI-5 | Modify Reservation | As a customer, I want to update my existing booking so that I can extend or shorten my rental period. | 5 | Medium | Sprint 2 | Not Started | Add modify button in dashboard. | Updates reflected correctly in records.
REP-1 | Car Usage Report | As a rental manager, I want to see which cars are most frequently rented so that I can manage fleet inventory. | 8 | High | Sprint 3 | Not Started | Decide report format (chart/table). | Shows top rented cars with counts.
REP-2 | Daily Rentals Report | As a rental manager, I want to view daily rental activity so that I can track business performance. | 5 | Medium | Sprint 3 | Not Started | Summarize bookings per day. | Daily rental totals display correctly.
SEC-1 | Secure Login | As a customer, I want to log in securely so that my personal data is protected. | 8 | High | Sprint 1 | Not Started | Use hashed passwords and input validation. | Login only succeeds with valid credentials.
Milestone 02 should now include:
Story ID, Title, Card (User Story) – already from Milestone 01 (You may add, or break down some of the story)
Story Points – estimated effort (e.g., 1, 3, 5, 8 using Fibonacci scale)
Priority (High, Medium, Low)
Sprint – which sprint it belongs to (Sprint 1, 2, or 3), the original Sprint
Status – Not Started, In Progress, or Done
Conversation – clarifications or notes from team discussions
Confirmation – acceptance criteria (how to know the story is “done”)
Note: The Fibonacci scale is a system of Agile estimation that uses numbers from the Fibonacci sequence (typically 0, 1, 2, 3, 5, 8, 13, 21, etc.) to assign story points to user stories and tasks.
This scale reflects an exponential increase in effort for more complex tasks and helps teams account for the growing uncertainty in estimating larger work.

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
UI-1 | UI-1.1 |  | <UI Epic 1, Task 1 description> |  | In Progress
UI-2 | UI-2.1 |  | <UI Epic 2, Task 1 description> |  | Completed
UI-2 | UI-2.2 |  | <UI Epic 2, Task 2 description> |  | Planned
COM-2 | COM-2.1 |  |  |  | Planned