## blog
[7 empty] | Team Members | [10 empty] | Instructions: Fill in only the green portions. For the activities table, put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Adjust the cell size to ensure all text is visible as needed. Add more rows as necessary
[7 empty] | First Name | Last Name | Nickname (max 6 characters)
[7 empty] | Pusarla V. | Sindhu | PV
[7 empty] | Robert | Marley | Bob
[7 empty] | Elizabeth | Windsor | Lizzie
[7 empty] | Samantha | Stevens | Sam
Joy
[7 empty] | Claude | Shannon | Claude
Activities Table
Date | Who | [5 empty] | Type of Activty | Number of hourse spent | Purpose | Output | Hours spent
| PV | Bob | Lizzie | Sam | Joy | Claude |  |  |  |  | PV | Bob | Lizzie | Sam | Joy | Claude
Milestone 1
2019-01-12 | 1 | 1 | 1 | 1 | 1 | 1 | Work at home | 3 | Think of opportunities | Input for jan 20 meeting | 3 | 3 | 3 | 3 | 3 | 3
2019-01-20 | 1 | 1 | 1 | 1 | 1 | 1 | meeting | 2 | Set mission statement | 3 opportunity statements. Rank. Write mission statement | 2 | 2 | 2 | 2 | 2 | 2
[10 empty] | Total hours | 5 | 5 | 5 | 5 | 5 | 5
[10 empty] | Total team hours | [6 empty] | 30
Milestone 2
2019-01-25 | 1 | [5 empty] | work at home | 3 | Create draft interview script | Draft interview script | 3 | 0 | 0 | 0 | 1 | 0
[10 empty] | Total hours | 3 | 0 | 0 | 0 | 1 | 0
[10 empty] | Total team hours | [6 empty] | 4
Sprint 1
2019-01-25 | 1 | 1 | 1 | 1 |  | 1 | Meet | 3 | Plan sprint 1 | Sprint 1 goal. Sprint backlog | 3 | 3 | 3 | 3 | 2 | 3
[10 empty] | Total hours | 3 | 3 | 3 | 3 | 2 | 3
[10 empty] | Total team hours | [6 empty] | 17
Sprint 2
2019-01-25 |  | 1 |  |  |  |  | Work in lab | 5 | Integrate motion sensor into project | Sensor data makes its way to serer and then to phone | 0 | 5 | 0 | 0 | 1 | 0
[10 empty] | Total hours | 0 | 5 | 0 | 0 | 1 | 0
[10 empty] | Total Team hours | [6 empty] | 6
Sprint 3
2019-01-25 | 1 | 1 | 1 | 1 |  | 1 | Prepare final demo | 2 | List all functionality to be demoed: What order to demo it? How to best demo each function? | Final Demo 10 minutes long | 2 | 2 | 2 | 2 | 2 | 2
[10 empty] | Total hours | 2 | 2 | 2 | 2 | 2 | 2
[10 empty] | total team hours | [6 empty] | 12
[10 empty] | Total hour over project | 13 | 15 | 10 | 10 | 11 | 10
[10 empty] | Total team hours over project | [6 empty] | 69